## Tabelle1
Task | Optimistic | Nominal | Pessimistic | Expectation | Variation | Finished Task | Optimistic | Nominal | Pessimistic
|  |  |  | 0 | 0 | Rearrange the data mining UI | 1 | 2.5 | 12
|  |  |  | 0 | 0 | Add annotations to mark methods for the function registry | 2 | 4.5 | 15
|  |  |  | 0 | 0 | Implement a FunctionRegistry | 3 | 7 | 25
|  |  |  | 0 | 0 | Implement a FunctionRetriever | 2 | 5 | 18
|  |  |  | 0 | 0 | Add persistence bundle for the data mining | 1 | 1.5 | 6
Replace static dimensions with @Dimension | 5 | 11 | 24 | 12.1667 | 3.1667
Implement a simple UI-Prototype for a function editor | 6.5 | 12 | 20 | 12.4167 | 2.25
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Total duration and variation |  |  |  | 24.5833 | 3.8846
Formatted duration |  |  | 1 | 0 | 0.58333
h: Hours
d: Days = 8 h
w: Weeks = 2.5 d